## Product Backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | USER STORIES | SCURM TEAM ASSIGNED | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
SPRINT-1 USER AUTHENTICATION
P001 | high | ID-001 | login | Admin team | yashasree |  |  | completed | NO
P002 | medium | ID-002 | username | Admin team
P003 | high | ID-003 | password | Admin team
SPRINT-2 Movie Search and Selection
P004 | high | ID-004 | movie search | Developer team | Sai charan
P005 | high | ID-005 | movie selection | Developer team |  |  |  | started | NO
SPRINT-3 Showtime and Seat Selection
P006 | high | ID-006 | showtime selection | Developer team | likitha |  |  | not started | NO
P007 | high | ID-007 | seat selection | Developer team
SPRINT-4 Booking and Payment
P008 | medium | ID-008 | booking ticket | Developer team | lahari |  |  | not started | NO
P009 | high | ID-009 | manage booking | Developer team
P010 | high | ID-010 | payment | Developer team
SPRINT-5 Cancellation and refund
P011 | high | ID-11 | cancel booking | cancellation team | sravya |  |  | not started
P012 | high | ID-12 | process refund | cancellation team |  |  |  | not started
P013 | medium | ID-13 | notify user cancellation | cancellation team |  |  |  | not started
SPRINT-6 Notifications
P014 | medium | ID-14 | notifications | notification team | divya |  |  | not started
SPRINT-7 Recommendations | medium | ID-15 | movie recommendations | recommendations team | divya |  |  | not started

## Sprint backlog
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION |  |  | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
|  | AS A<type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal>
P001 | login | as a user can login | By entering credentials:input username /email and password in designated fields | so that user can enter their username and password securely | Yashasree | 22 days | 21days | completed | No
|  |  | click LogIn Button | Initiate the Login process once users entered their credentials
|  |  | if user forget their password | user canrecover their account acess if they forgot thie password
P002 | username | as a user I want to manage my username in application | user can view current username | users can easily access information about their existing username for reference and verification | Yashasree | 32 days | 29 days | Inprogress | No
|  |  | user can edit their username | empower users to update their username to reflect changes in their personel information
|  |  | user can validate new username | prevent users from entering invalid usernames by validating the format and length of the new username
|  |  | user can save changes | enable users to finalize their changes by saving the updated username in the system
P003 | password | As a user I want to manage my password securely | users can change password | users can maintain control over their account security by providing a straightforward method to change passwords | Yashasree | 20 days | 18days | Completed | no
|  |  | validate passwords | users can enhance account security by enforcing password strength criteria to mitigate the risk og unauthorized access
P004 | Movie search | user can search | implement a search bar where users can enter movie titles | users can able to find specific movies easily by searching for their titles | Sai charan | 2days | 2 days | completed | No
P005 | movie selection | As a user can select movies by performing | user can browse movies | Allow users to visually browse through available movies quickly | Divya | 10 days | 7days | Inprogress | No
|  |  | add filter options such as gnere,rating,release date | Allow uses to narrow down their movie choices based on their preferences
|  |  | watch movie trailers | users to preview movies by watching their trailers directly within the app
P006 | Show time selection | as a user we can select and performtask for book tickets | user can select show time | uers can easily view and select from available showtimes | likitha | 12days | 11days | Inprogress | No
|  |  | select desired format(2D,3D) | users can choose theirprefereedviewing format for an optimal movie experience
P006 | screen selection | as a user we can select screen and seat layouts categories | view seating Layout | user can see the interactive seat map | likitha | 12 days | 11days | completed | No
|  |  | select seats | user can click on available seats to select and confirm selected seats by clicking next or continue
|  |  | view Pricing | user can see the cost associated with their selected seats before proceeding
P008 | booking ticket | as a user ,want book ticket | Implement Movie selection | user ca browse available movies,view details,select the movie they want to book ticket for | lahari | 12 days | 10 | completed | No
|  |  | Showtime selection | user can choose the date and time of movie show they wish to attend
|  |  | seat selection | user can achive interactive seating map to select their preferred seats for the chosen showtime
|  |  | Ticket Quality selction | Allow users to specify the number of tickets they want to purchase for the selected movie and showtime
[5 empty] | lahari | 20 days | 18 days | Inprogress | No
P009 | manage booking | As a user ,I want to manage booking by searching,viewing | Develop Remainders and notifications | user can achieve remainders and notifictions about their upcoming bookings,ensuring they don’t mss their schedule
|  |  | Implement Booking History | user can achieve comprehensive booking history,including details of past transactions and ticketspurchased
|  |  | Enable Modification of Bookings | Allow users to modify their bookings such as changing the ovie showtime,selecting different seats,or adding/removing tickets
|  |  | Implement Booking Management Functionality | users can view their booking history,upcoming bookings,and details such as movie title,showtime andseat selection
P0010 | payment | As a user ,I want to perform payment that involved in different payment methods | user can perform Reasearch payment options | user can identify and select payment gateways that offers a balance between functionality ,affodability with target audiences regoins | Lahari | 10 days | 9 days | completed | No
|  |  | user can Experience Requirements | user can define clear, intuitive payment flows that guide throgh the transaction process seamlessly,ensuring a positive user experience
|  |  | Test payment Flows | identify and resolve any usability issues,bugs,performance bottlenecks within the payment process to ensure smooth and reliable transactions
|  | As a user ,I want to be able to cancel my movie ticket booking if I change my plans or no longer want to attend | as a user we can see a cancel booking button on their booking details page | user can prompted with a confirmation dialog beforefinalizing the cancellation
P011 | Cancel Booking |  | Update booking status in the database | upon cancellation the booking status is updated to cancelled in the database | Sravya | 7 days | 6 days | completed | No
|  |  | Send a cancellation confirmation email | user receives a confirmation email regarding the cancellation
P012 | Process refund | As a user , I want to be able to request a refund for my movie | Request a Refund | user can cancel a booked movie ticket and initiate a refund request | Sravya | 25 days | 23 days | Completed | No
|  |  | check Refund status | user can Monitor the progress of a submitted refund request
|  |  | understand Refund Policy | user can gain knowledge of the eligibility criteria and conditions for obtaining a refund
|  |  | Receive Refund Confirmation | user can get confirmation that a refund has been processed successfully
|  |  | Contact support for Refund Issues | user can Resolve any problems or delays encountered during the refund process.
ID-14 | Notification Team | As a user, I want to receive notifications about my booked tickets | setup notification service integration | so that i can achieve the application to send notifications to users devices | Divya | 1 to 2 weeks | 1.5 weeks | Completed | No
|  |  | Design notigication teplates for different ticket statuses(booking confirmed,payment pending,cancellation | crafting well designed notification templates ensures user receive clear and informative notifications about their booked tickets.
|  |  | Implement backend logic to trigger notifications based on ticket status changes | enables the application to automatically send notifications based on changes in ticket changes so that user receive timely updates about their bookings without the need for manual intervention
|  |  | Test notification delivery on different devices and platforms | user can achieve that notifications feature functions correctly and reliably for all.